## Blad1
Work Breakdown Structure Element |  |  | Task | Responsible team member | Status | Week 1 |  | Week 2 |  | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 |  | ….
[6 empty] | 2022-10-17 | 2022-10-20 | 2022-10-24 | 2022-10-27 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-08 | …. | 2022-01-09
CEDAR | Bulk input tool | Problem analysis | Worksession Mariam Basajja | Hielke, Kenneth | In progress | [11 empty] | ….
|  |  | Setup of local bulk input tool | Hielke, Kenneth | Done | [11 empty] | ….
|  | Solution | Worksession Mariem Ghardallou | Hielke, Kenneth | Cancelled | [11 empty] | ….
|  |  | Documentation | Hielke, Kenneth | To be done | [11 empty] | ….
| Linking of datasets |  | Explore Nigerian dataset | tbd | To be done | [11 empty] | ….
|  |  | Query other dataset | tbd | To be done | [11 empty] | ….
Data analysis | Infrastructure |  | Setup Google Colabs | Kenneth | Done | [11 empty] | ….
| Media dataset | Preprocessing | Preprocessed data | Milou, Hielke, Kenneth | Done | [11 empty] | ….
|  |  | Explanation of choices | Milou, Hielke, Kenneth | Done | [11 empty] | ….
|  | Visualisation | First visualisations | Milou, Danielle | To be done | [11 empty] | ….
|  |  | Feedback session from Mariem Ghardallou | Milou, Christie | To be done | [11 empty] | ….
|  |  | Adjusted visualisations | Milou | To be done | [11 empty] | ….
|  | Initial analysis | Short presentation/report | Milou | To be done | [11 empty] | ….
| Interview dataset | Preprocessing | Preprocessed data | Milou, Hielke, Kenneth | Done | [11 empty] | ….
|  |  | Explanation of choices | Milou, Hielke, Kenneth | Done | [11 empty] | ….
|  | Visualisation | First visualisations | Kenneth, Hielke | In progress | [11 empty] | ….
|  |  | Feedback session from Mariem Ghardallou | Milou, Christie | To be done | [11 empty] | ….
|  |  | Adjusted visualisations | Christie | To be done | [11 empty] | ….
|  | Initial analysis | Short presentation/report | Christie | To be done | [11 empty] | ….
| Combined insights from datasets | Visualisation | Assess correlations in data | Hielke, Danielle | To be done | [11 empty] | ….
First visualisations
|  |  | Feedback session from Mariem Ghardallou | Hielke, Danielle | To be done | [11 empty] | ….
|  |  | Adjusted visualisations | Hielke, Danielle | To be done | [11 empty] | ….
|  | Initial analysis | Short presentation/report | Hielke, Danielle | To be done | [11 empty] | ….
Class deliverables | Technical Plan |  | Create Gantt chart | Christie | Done |  | x | [9 empty] | ….
|  |  | Create WBS | Christie | Done |  | x | [9 empty] | ….
|  |  | Describe gantt chart and wbs | Milou | Done |  | x | [9 empty] | ….
|  |  | Describe approach to technical plan | Danielle | Done |  | x | [9 empty] | ….
| Data managment plan |  | Data management plan | Christie, Danielle | Done |  |  |  | x | [7 empty] | ….
|  |  | Ethical conciderations | Christie, Danielle | Done |  |  |  | x | [7 empty] | ….
|  |  | Legal conciderations | Christie, Danielle | Done |  |  |  | x | [7 empty] | ….
| Final Presentation |  | tbd | tbd | To be done | [10 empty] | x
| Final Report |  | tbd | tbd | To be done | [12 empty] | x