## Blad1
[5 empty] | September | [8 empty] | Oktober | [26 empty] | November | [18 empty] | December |  |  |  |  | Januari
Work Breakdown Structure Element |  | Task | Responsible team member | Status | Week 1 |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 | [6 empty] | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  | Week 12 |  | Week 13 | Week 14 | Week 15 | Week 16
[5 empty] | 19 |  |  |  | 26 |  |  |  |  | 3 |  |  |  |  | 10 | [6 empty] | 17 |  |  |  |  | 24 |  |  |  |  | 31 |  |  |  |  | 7 |  |  |  |  | 14 |  |  |  |  | 21 |  |  |  |  | 28 |  |  |  | 5 |  | 12 | 19 | 26 | 2 | 9
CEDAR | Bulk input tool | Worksession Mariam Basajja | Hielke, Kenneth | In progress | [31 empty] | . | . | . | . | .
|  | Worksessions Samson | Kenneth, Hielke | To be done | [40 empty] | . | . | . | . | . | .
|  | Worksession Mariem Ghardallou | Hielke, Danielle | To be done | [46 empty] | . | . | . | .
|  | Setup of local bulk input tool | Hielke, Kenneth | Done | [21 empty] | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
|  | Testing Bulk input tool | Hielke | In progress | [40 empty] | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
|  | Documentation | Hielke, Kenneth | To be done
Data analysis | Infrastructure | Setup Google Colabs | Kenneth | Done | [14 empty] | . | . | . | . | . | . | .
| Media dataset | Preprocessed data | Milou, Hielke | Done | [21 empty] | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
|  | Explanation of choices | Milou, Hielke | Done | [21 empty] | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
|  | Further data processing based on plots | Milou, Danielle | In progress | [45 empty] | . | . | .
|  | First visualisations | Milou, Danielle | To be done | [40 empty] | . | . | . | . | .
|  | Review Analysis | Hielke, Kenneth | To be done | [47 empty] | . | . | .
|  | Create advanced plots | Milou, Christie | Done | [47 empty] | . | . | . | . | . | . | . | .
|  | Cleanup and design of plots | Hielke | In progress | [50 empty] | . | . | . | . | .
|  | Adjusted visualisations | Milou | To be done
|  | Short presentation/report | Milou | To be done
| Interview dataset | Preprocessed data | Kenneth | Done | [21 empty] | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
|  | Explanation of choices | Kenneth | Done | [22 empty] | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | . | .
|  | First visualisations | Kenneth | In progress | [40 empty] | . | . | . | . | .
|  | Advanced Visualisations | Hielke, Kenneth | To be done | [45 empty] | . | . | . | . | . | . | . | . | . | .
|  | Cleanup and design of plots | Kenneth | In progress | [50 empty] | . | . | . | . | .
|  | Analysis of visualisations | Danielle | To be done | [47 empty] | . | . | .
|  | Short presentation/report | Christie | To be done
Class deliverables | Report on meeting | Specify project goals and imputs | All | [5 empty] | . | . | . | . | .
|  | Report on meeting with Team and guides | All | Done |  | x
| Canvas | Create Canvas | All | Done |  |  | . | . | . | X
| Problem Exploration | Read articles | Christie | [10 empty] | . | . | . | . |  |  |  |  | x
|  | Prepare interviews | Milou,Danielle | [10 empty] | . | . | . | . |  |  |  |  | x
|  | Do interviews | All | [12 empty] | . | . | . | . |  |  | x
|  | Write assignment | All | [16 empty] | . | . | x
| Technical Plan | Assign Roles | All |  |  |  | .
|  | Create Gantt chart | Christie | Done | [14 empty] | . | . | . | . | . | . | . |  |  |  | x
|  | Create WBS | Christie | Done | [14 empty] | . | . | . | [7 empty] | x
|  | Describe gantt chart and wbs | Milou | Done | [21 empty] | . | . | . | x
|  | Describe approach to technical plan | Danielle | Done | [21 empty] | . | . | . | x
| Data managment plan | Data management plan | Christie, Danielle | Done | [29 empty] | x
|  | Ethical conciderations | Christie, Danielle | Done | [29 empty] | x
|  | Legal conciderations | Christie, Danielle | Done | [29 empty] | x
| Final Presentation | Create framework | Danielle | To be done | [46 empty] | . | . | . | . | [6 empty] | x
x
| Final Report | Problem exploration | Danielle | To be done | [50 empty] | . | . | . | . | . | [6 empty] | x
|  | Plan | Christie | [51 empty] | . | . | . | . | . | [6 empty] | x
|  | Implementation Fair | Kenneth | [51 empty] | . | . | . | . | . | [6 empty] | x
|  | Implementation preprocessing | Milou | [62 empty] | x
|  | Implementation Visualisations | [63 empty] | x
|  | Implementation bulk imput tool | [63 empty] | x
|  | Team and expertise | [63 empty] | x
|  | Meeting with Mustafa |  |  |  | . | [59 empty] | x
|  | Discussion | [63 empty] | x
|  | Concusion | [63 empty] | x
|  | Recommendation | [63 empty] | x
|  | Personal assessement | [63 empty] | x
x